## Slide 1
Fixed-income pricing system: progress to 19 September 2026
• Built for the client's fixed-income portfolio
• Presented by [YOUR NAME] and Mario [SURNAME] — fill these in
• Twelve weeks of work, 26 June to 19 September 2026
Notes: Keep this up for ten seconds. No preamble.

## Slide 2
What we were asked to build, and where it stands
• The client had a pricing toolkit built in Excel and Visual Basic, grown over years, that only a handful of people could run or change
• The job: rebuild it as proper software — same answers, but testable, automatable, and able to be handed to their own engineering team
• Status: the system works end to end and is in use. The remaining work is extending it to the rest of the portfolio
Notes: Two things to land here. First, this was never a research project — it is a rebuild of something that already ran the client's business, so "does it give the same answers" was always the test. Second, the thing exists and runs today; we are not describing a plan.

## Slide 3
What it does today
• Takes a bond, the market rates for that day, and the price the client's custodian recorded — and works out what the market is charging that borrower, and how much the bond's value moves when rates move
• Runs from a spreadsheet, from a command line, or as a service the client's own systems can call — same answer from all three
• Every result is reproducible: run it again a month later and you get the identical file, to the byte
• We price the client's March 2009 book — their own reference case, chosen because the outcomes are already known
Notes: The third point is worth a sentence. In a pricing system that number is the whole product, so we made "did anything change" a mechanical check rather than a matter of opinion. Every time we change the code, every price the system has ever published is regenerated and compared. That is how we can tell you a restructuring changed nothing.

## Slide 4
Coverage
• All six classes of ordinary bonds are complete — corporate, government, municipal, agency, inflation-linked, guaranteed
• The single largest remaining block is not waiting on us
Notes: The honest reading of this chart is the second bullet. Of what is left, roughly eight securities in ten are blocked on data we have formally requested, and two in ten are work we have scoped but not started. That distinction is the whole message of this meeting.
For reference:
securities
**Priced today** | **766** | every ordinary bond in the portfolio
Waiting on data we have asked for | 1,046 | 882 mortgage securities + 164 bonds whose terms are not in the file we were given
Scoped, not yet built | 412 | the other pooled products
Excluded by the client, or out of scope | 36

## Slide 5
How we know the numbers are right
• A government bond priced on its own government's curve must come out at zero. Japan's come out at 0.0; the UK's at 0.04% — the thermometer reads right in ice water
• The client's own custodian independently reports a risk number for some bonds. Where it does, ours agrees — four of five agency bonds within a tenth of a year
• We re-derived the client's own inflation adjustments from published government statistics — thirteen US inflation-linked bonds, agreeing to six parts in a million
Notes: None of these three checks uses anything we control. That is the point — we are not grading our own homework. The third one also caught something: the client's records are struck one day after the valuation date. Small, but nobody knew it.

## Slide 6
The one thing blocking the largest block
• 882 mortgage securities — 39% of the portfolio — need terms that only Bloomberg has
• The engine for them is already built and tested. It has been waiting on data, not on code — the day the data lands it runs with no further development
• Requested 22 July 2026. [STATUS — confirm the week of presenting; see the note]
• A second, smaller request covers 164 ordinary bonds whose terms are missing from the file we were given
Notes: This is the slide we would most like you to remember. There is no technical obstacle and no disagreement about what is needed. Four in ten securities in this portfolio become priceable on work that is already finished, as soon as the terms arrive. BEFORE PRESENTING, REPLACE THE THIRD BULLET. As of 19 September we had word the data may just have been delivered, unverified. Use whichever is true on the day. If it has NOT arrived: "Requested 22 July 2026 — still outstanding." The ask is that you help move it. If it HAS arrived: "Requested 22 July; the data reached us in September and we are loading it now." That is the better version of this slide — the engine was built ahead of the data and the largest remaining block is unlocking rather than stuck. Do not leave the outstanding wording standing once it is false. An investor who later learns the data had already arrived will discount everything else on these slides. Say all of this without blame either way. The request went to the client; we are surfacing it, not escalating it. If asked why it took this long, the honest answer is we do not know.

## Slide 7
What is left
• Mortgage-backed securities — engine built, awaiting data (882)
• The other pooled products — collateralised mortgage obligations, asset-backed, commercial mortgage-backed. Scoped; each reuses machinery that already exists (412)
• A portfolio-level credit risk layer — in the original brief, not yet started
• We are not blocked on anything in the second and third items except sequencing
Notes: Be straight that the 412 is genuine remaining work, not a data problem. What makes it tractable is that the hard parts — the cash-flow machinery, the option model, the market data plumbing — are built and proven on the 766.

## Slide 8
Handover
• The client asked for the code to be restructured so their own engineering team can take it over — that restructuring is complete
• It runs unchanged on their cloud platform, so the whole team can use it rather than one machine
• Everything ships with the data and the instructions to reproduce it — nothing depends on us being in the room
Notes: This matters commercially. The deliverable is not a service they have to keep buying; it is an asset they own and can run. That was the brief and it is met.